## Ark1
Tasks | Responsible | Involved People
Start Phase
Initial Meeting | Project Manager | Project Manager
Planning | Project Manager | Front-End Dev
Research | Designer | Designer
Content Strategy | Project Manager | Journalist
Content Planing | Developer | Photographer
Site Outline | Design/Dev
Design Phase
sketching | Designer
Illustration | Designer
Structure | Design/Dev
Text Content | Journalist
Site Photos | Photographer
Key meeting 1 | Project Manager
Build Phase
Wireframe | Designer
Employees pic | Photographer
Site Build | Developer
UI Planning | Design/Dev
Key Meeting 2 | Project Manager
Testing | Developer
Release Phase
UI Testing | Developer/Designer
Content Validation | Journalist
Refinement | Developer/Designer
Key Meeting 3 | Project Manager
Launch | Design/Dev/PM

## Ark2
Task | Work Days | Start Date | End Date
Initial Meeting | 1 | 2019-03-10 | 2019-03-11
Planning | 3 | 2019-03-12 | 2019-03-15
Research | 5 | 2019-03-16 | 2019-03-21
Content Strategy | 1 | 2019-03-22 | 2019-03-23
Content Planing | 1 | 2019-03-24 | 2019-03-25
Site Outline | 2 | 2019-03-26 | 2019-03-28
sketching | 3 | 2019-03-29 | 2019-04-01
Illustration | 3 | 2019-04-02 | 2019-04-05
Structure | 2 | 2019-04-06 | 2019-04-08
Text Content | 5 | 2019-04-09 | 2019-04-14
Site Photos | 2 | 2019-04-15 | 2019-04-17
Key meeting 1 | 1 | 2019-04-18 | 2019-04-19
Wireframe | 3 | 2019-04-20 | 2019-04-23
Employees pic | 2 | 2019-04-24 | 2019-04-26
Site Build | 20 | 2019-04-27 | 2019-05-17
UI Planning | 2 | 2019-05-18 | 2019-05-20
Key Meeting 2 | 1 | 2019-05-21 | 2019-05-22
Testing | 3 | 2019-05-23 | 2019-05-26
UI Testing | 5 | 2019-05-27 | 2019-06-01
Content Validation | 2 | 2019-06-02 | 2019-06-04
Refinement | 3 | 2019-06-05 | 2019-06-08
Key Meeting 3 | 1 | 2019-06-09 | 2019-06-10
Launch | 1 | 2019-06-11 | 2019-06-12
Formulas:
End Date = [Start Date]+[Work Days]
Start Date = [End Date, row above]+1

## Ark3
Start Phase | Strategy | Build | Launch