## Ark1
Tasks | Responsible | Involved People
Start Phase
Initial Meeting | Project Manager | Project Manager
Planning | Project Manager | Front-End Dev
Research | Designer | Designer
Content Strategy | Project Manager | Journalist
Content Planing | Developer | Photographer
Site Outline | Design/Dev
Design Phase
sketching | Designer
Illustration | Designer
Structure | Design/Dev
Text Content | Journalist
Site Photos | Photographer
Key meeting 1 | Project Manager
Build Phase
Wireframe | Designer
Employees pic | Photographer
Site Build | Developer
UI Planning | Design/Dev
Key Meeting 2 | Project Manager
Testing | Developer
Release Phase
UI Testing | Developer/Designer
Content Validation | Journalist
Refinement | Developer/Designer
Key Meeting 3 | Project Manager
Launch | Design/Dev/PM